## Slide 1: Squeezer Update
February 10, 2010
H1 Squeezer Experiment
ANU, AEI, MIT, CIT and LHO collaboration

## Slide 2: Progress
On budget & no major roadblocks so far
  No major schedule setback (maybe ~2 month behind with optics procurement)
  2nd update review was held on February 9
New postdoc (Lisa B.)
Lasers ready at MIT; locked together
OPO ready at ANU with 5-6dB of squeezing
  Ready to ship in March, required in early May
Electronics is 80% complete; will be done by May
Developed a noise and servo model
Next: Set up the AEI SHG at MIT

## Slide 4: ANU Traveling wave OPO