## Sheet1
|  | Start | Stop | Comletion | Comment
Fiber Launch System | 452 days | 2009-06-02 08:00 | 2011-02-23 17:00 | 30% | Fiber stabilization eliminated from design
Fiber and coupling | 5 mons | 2009-06-02 08:00 | 2009-10-19 17:00 | 50% | input end availabe in same lab
Stabilization: optical setup | 3 mons | 2009-10-20 08:00 | 2010-01-11 17:00 |  | task eliminated; not needed
Stabilization: electronics | 3 mons | 2009-10-20 08:00 | 2010-01-11 17:00 |  | task eliminated; not needed
Performance characterization | 3 mons | 2010-01-12 08:00 | 2010-04-05 17:00 |  | task eliminated; not needed
Integration into squeezer | 2 mons | 2010-04-06 08:00 | 2010-05-31 17:00 | 0% | will probably be done in February
Installation on H1 | 7 days | 2011-02-15 08:00 | 2011-02-23 17:00 | 0%
Squeezer | 641 days | 2008-09-29 08:00 | 2011-03-14 17:00
Housing, location, breadboard, laser safety | 4.5 mons | 2008-09-29 08:00 | 2009-01-30 17:00 | 100%
Optical layout | 4.5 mons | 2009-02-02 08:00 | 2009-06-05 17:00 | 100% | updated when necessary
Main dual wavelength laser purchase | 6 mons | 2008-09-29 08:00 | 2009-03-13 17:00 | 100% | use a LIGO I laser
Main dual wavelength laser characterization | 1 mon | 2009-03-16 08:00 | 2009-04-10 17:00 | 100% | use a LIGO I laser
Auxiliary locking laser purchase | 5 mons | 2008-09-29 08:00 | 2009-02-13 17:00 | 100%
Auxiliary locking laser characterization | 1 mon | 2009-02-16 08:00 | 2009-03-13 17:00 | 100% | JDSU NPRO
Laser locking opto-electronics main laser | 4 mons | 2008-09-29 08:00 | 2009-01-16 17:00 | 90% | acutually locking to fiber not done yet, but identical to aux. laser
Laser locking opto-electronics auxiliary laser | 2 mons | 2009-01-19 08:00 | 2009-03-13 17:00 | 100%
Laser locking commissioning | 2 mons | 2009-06-08 08:00 | 2009-07-31 17:00 | 70% | main laser locking is identical to aux. laser locking
OPO purchase | 4 mons | 2008-09-29 08:00 | 2009-01-16 17:00 | 90% | everything availble and tested; TBD: superpolished optics
OPO assembly and testing | 6 mons | 2009-01-19 08:00 | 2009-07-03 17:00 | 100%
OPO locking opto-electronics | 2 mons | 2009-03-16 08:00 | 2009-05-08 17:00 | 50% | done at ANU; hardware available or on order at MIT
OPO commissioning | 4 mons | 2009-08-03 08:00 | 2009-11-20 17:00 | 100% | done at ANU
Squeezer phase locking opto-electronics | 3 mons | 2009-05-11 08:00 | 2009-07-31 17:00 | 20% | not required until April at MIT; done at ANU
Local oscillator phase locking opto-electronics | 2 mons | 2009-08-03 08:00 | 2009-09-25 17:00 | 20% | not required until April at MIT; done at ANU
Homodyne test diodes | 6 mons | 2008-09-29 08:00 | 2009-03-13 17:00 | 100% | detector from AEI at ANU
Light baffles and dumps | 6 mons | 2009-06-08 08:00 | 2009-11-20 17:00 | 10% | will be installed/designed as assembly progresses
Remote Controls | 3 mons | 2010-01-12 08:00 | 2010-04-05 17:00 | 20% | hardware design done; 30% assembled; software setup TBD
Squeezing commissioning | 4 mons | 2009-12-15 08:00 | 2010-04-05 17:00 | 50% | ANU part done; MIT part starts in May
System characterization and acceptance | 2 mons | 2010-04-06 08:00 | 2010-05-31 17:00 | 0% | Expected: OPO at MIT in May; SHG mirrors at MIT in April
Ship to LHO | 2 mons | 2010-06-01 08:00 | 2010-07-26 17:00 | 0%
Rebuild at LHO | 1 mon | 2010-07-27 08:00 | 2010-08-23 17:00 | 0%
Characterization at LHO | 3 mons | 2010-08-24 08:00 | 2010-11-15 17:00 | 0%
Installation on H1 | 1 mon | 2011-02-15 08:00 | 2011-03-14 17:00 | 0%
Faraday | 627 days | 2008-09-29 08:00 | 2011-02-22 17:00
Optical layout and mechanical drawings | 6 mons | 2008-09-29 08:00 | 2009-03-13 17:00 | 100%
Purchase and inspection | 3 mons | 2010-08-31 08:00 | 2010-11-22 17:00 | 0%
Assembly | 1 mon | 2010-11-23 08:00 | 2010-12-20 17:00 | 0%
Characterization | 2 mons | 2010-12-21 08:00 | 2011-02-14 17:00 | 0%
Acceptance | 1 day | 2011-02-15 08:00 | 2011-02-15 17:00 | 0%
Installation on H1 | 1 wk | 2011-02-16 08:00 | 2011-02-22 17:00 | 0%
Auto-alignment (optional): | 405 days | 2009-08-25 08:00 | 2011-03-14 17:00 |  | not in the plans
Tip-tilt steering optics and interface | 4 mons | 2009-08-25 08:00 | 2009-12-14 17:00
Wavefront sensors electronics | 6 mons | 2009-12-15 08:00 | 2010-05-31 17:00
Servo electronics | 3 mons | 2010-06-01 08:00 | 2010-08-23 17:00
Test and Characterization | 2 mons | 2010-08-24 08:00 | 2010-10-18 17:00
Installation on H1 | 1 mon | 2011-02-15 08:00 | 2011-03-14 17:00
Experimental test: | 115 days | 2011-02-23 08:00 | 2011-08-02 17:00
Faraday checkout | 1 wk | 2011-02-23 08:00 | 2011-03-01 17:00 | 0%
Squeezer performance test on location | 1 mon | 2011-03-15 08:00 | 2011-04-11 17:00 | 0%
Squeezer alignment and mode matching | 1 mon | 2011-04-12 08:00 | 2011-05-09 17:00 | 0%
Squeezed light injection and noise characterization | 2 mons | 2011-05-10 08:00 | 2011-07-04 17:00 | 0%
Auto-alignment commissioning (optional) | 1 mon | 2011-07-05 08:00 | 2011-08-01 17:00 | 0%
Experimental test completed | 1 day | 2011-08-02 08:00 | 2011-08-02 17:00 | 0%
Modelling Support: | 440 days | 2008-08-04 08:00 | 2010-04-09 17:00
Optical beam path | 6 mons | 2008-08-04 08:00 | 2009-01-16 17:00 | 75% | still working on mode matching solutions
Optical scattering paths and effects | 6 mons | 2009-01-19 08:00 | 2009-07-03 17:00 | 100% | noise and servo model done
H1 interferometer model | 3 mons | 2009-07-06 08:00 | 2009-09-25 17:00 | 100% | noise and servo model done
Updated H1 noise model | 1 mon | 2009-09-28 08:00 | 2009-10-23 17:00 | 100% | noise and servo model done
Advanced LIGO interferometer model | 6 mons | 2009-10-26 08:00 | 2010-04-09 17:00 | 0% | not in a hurry