## Slide 1
E1000304-v3 aLIGO SEI Testing and Commissioning Overall Plan
Components and Sub-Assemblies Testing
Electronics
Actuators
Sensors
Vacuum Pods
Modules Testing (HEPI, HAM-ISI, BSC-ISI)
Phase I: Assembly Validation
Phase II: Integration
Phase III: Control Commissioning
Chamber Validation
Operations

## Slide 2
Components and Sub-Assemblies Testing
Electronics: E1100876 - aLIGO SEI Electronics Testing Reports and Procedures
T1100453 - Ham 2&3 System Test Plan
  S1105160 - LHO ISI Test Stand Results
Inst. Main Page: E1100786 - aLIGO SEI Instruments, Testing Documents and Tracking Lists
Actuators: E1100338 - aLIGO LHO HEPI Actuators Tests Results
T1100234 - aLIGO Small Actuator Test Results from Qinetiq
T0900564 - aLIGO Large Actuator Test Results from Qinetiq
E1100741 - aLIGO BSC-ISI, Actuators Installation Location
Sensors: E1000257 - aLIGO HAM-ISI Capacitance Position Sensor Testing
E1100231 - aLIGO BSC-ISI Capacitance Position Sensor Testing
E1100326 - aLIGO T 240 seismometers for BSC-ISI
E1100397 - aLIGO GS-13 testing
E1000136 - aLIGO L4C Status Chart
Pods: E1100396 - aLIGO Seismometer Pods Neon Leak Test Results
Instrumentation: E1100740 - aLIGO BSC-ISI, Seismometers Installation Location
E1100770 - In-Vacuum Cabling Status for BSC6, BSC8, HAM2, HAM3
E1100822 - aLIGO BSC-ISI, Cables inventory and Installation Location

## Slide 3
HEPI Modules (33)
HAM-ISI Modules (15)
Phase I: Assembly Validation
Mechanical Assembly
No particular testing
Install Leads Validate
Phase I: Assembly Validation
Full Assembly
Generic procedure
- Validated per test results and report
BSC-ISI Modules (15)
Phase II: Integration
Simplified side chamber testing if no instrumentation change after Phase I.
Thorough side chamber testing if instrumentation modified after Phase I.
Insertion in the chamber
Integration with optical components
Unit specific testing, function of optics installation sequence.
Phase II finishes when we close the chamber.
Phase III: Control Commissioning
Generic Step by Step procedure
Several levels of performance
Acceptance criteria
Phase I: Assembly Validation
Full Assembly
Generic procedure
- Validated per test results and report
Operation
Phase II: Integration
Check HEPI is ready to receive an ISI platform (Stack, HAM-ISI or BSC-ISI)
Install ISI platform on HEPI
Leveling
Connect Actuators
Generic procedure to check and validate HEPI
Phase II finishes when we close the chamber.
Phase III:
Control Commissioning
Generic Step by Step procedure
Acceptance criteria
Operation
Phase II: Integration
Install on stand, balance and check functionalities
Integration with optical components
Unit specific testing, function of optics installation sequence.
Cartridge installation
Post insertion testing
Phase II finishes when we close the chamber.
Phase III: Control Commissioning
Generic Step by Step procedure
Several levels of performance
Acceptance criteria
Operation
Modules Testing Overview
Transport to IFO
Transport to IFO
Instrumentation
Close the chamber
Close the chamber
Close the chamber
Meet acceptance criteria.
Meet acceptance criteria.
Meet acceptance criteria.

## Slide 4
Phase I: Assembly Validation
HEPI
Overview: Mechanical assembly (no Instruments)
No particular tests (rigid connection between cross beams and piers). No report.
Final check is the leveling.
Assembly validation is responsibility of SEI installation lead (Jeremy @ LLO, Hugh @ LHO)
HAM-ISI
Overview: Sub-assembly check, Inventory, Balancing, Check & adjust gaps, Range of motion, Static tests, Linearity tests, Power spectrums, Transfer functions…
Main page: E1000305 - aLIGO HAM-ISI Testing and Commissioning Documentation
Procedure: E1000309 - aLIGO HAM-ISI, Pre-integration Testing Procedure, Phase I (post-assembly)
Report Example: E1000326 - aLIGO HAM-ISI, Pre-integration Test Report, Phase I, LLO Unit #2
BSC-ISI
Overview: Similar to HAM-ISI. Twice many stages.
Main page: E1000306 - aLIGO BSC-ISI Testing and Commissioning Documentation
Procedure: E1000486 - aLIGO BSC-ISI Testing Procedure, Phase I (Post-assembly)
Report Example: E1100294 - aLIGO BSC-ISI, Pre-integration Test Report, Phase I, LHO Unit #1

## Slide 5
Phase II: Integration
Everything between the end of the module assembly and closing the chamber.
In other words, all the testing related to merging with other modules
HEPI
Overview: Check that HEPI is ready to receive an ISI or Stack (Stops, Leveling…)
Check actuators and sensors (L4C power spectrums, IPS DC values…)
Install ISI (or passive stack)
Unlock HEPI. Monitor dial indicators, load cells.
Level HEPI.
Connect actuators.
Set IPS gaps.
Check the control software (SEI and SUS Watch dogs)
Test HEPI (Range of motions, Transfer functions, turn on low performance loops)
Leveling, alignments.
Report and validation of phase II.

## Slide 6
Phase II: Integration
Everything between end of the module assembly and closing the chamber
In other words, all tests related to merging with other modules
HAM-ISI
Phase II starts when the HAM-ISI unit is mounted on a stand in the observatory (LVEA or End Station)
Two-case scenario:
Assembly already completed and fully tested in the assembly building (i.e. HAM-ISI 8 & 9 @ LHO)
Minimum side chamber testing before insertion (DC values of CPS, power spectrums of GS13s…) . Could be done without electronic rack if not available. Testing completed after the chamber is closed.
Assembly completed in LVEA or End Station (Install GS13, CPS Shield…)
Need Side Chamber Testing before Installation.
After installation in the chamber:
- Platform is being populated with optics
- Testing sequence to be detailed chamber per chamber.
Report, Validation
Close the chamber: End of Phase II
Phase III: Control Commissioning

## Slide 7
Phase II: Integration
Everything between end of the module assembly and closing the chamber
In other words, all tests related to merging with other modules
BSC-ISI
Phase II starts when the BSC-ISI unit is mounted on stand in the observatory (LVEA or End Station)
Check functionalities (Static Tests, Transfer functions). Compare with measurements after assembly (Phase I)
Test control functionalities (Damping, Level 1 control…)
Integration with optical components. Testing is chamber specific, function of the optics installation sequence.
Installation in the chambers
Test basic control functionalities in the chamber (Damping, Level 1 control…)
Report, Validation
Close the chamber: End of Phase II
Phase III: Control Commissioning

## Slide 8
Phase III: Control Commissioning
Everything after closing the chamber and before hand-off to operations
HEPI: Control strategy developed for iLIGO
Detailed step by step procedure based on the BSC-ISI model
Being tested at LASTI
Procedure being written
HAM-ISI: Control strategy developed for eLIGO
Step by Step procedure based on the BSC-ISI model
Being tested at LASTI
Procedure being written
BSC-ISI: Control strategy developed on ETF and BSC-ISI prototype
Step by Step procedure
Tested at LASTI

## Slide 9
Performance Levels
HEPI
Basic control functionality tests during HEPI checkout (Phase II)
Regular performance control loops, Sensor Correction (Phase III)
HAM-ISI and BSC-ISI
Low Frequency control:
High Blend: Low performance ~ 1 Hz Blend frequency Phase II
Medium Blend: Medium Performance ~ .3 Hz Phase III
Low Blend: High Performance ~.1 Hz Phase III
High Frequency Control:
Control Level 1 : Low performance ~ 10 Hz Unity gain frequency Phase II
Control Level 2 : Medium Performance ~ 20 Hz Unity gain frequency Phase III
Control Level 3 : High Performance ~ 30 Hz Unity gain frequency Phase III