## Slide 1: Integration Planning
April 25, 2011
Valera Frolov, Daniel Sigg, Peter Fritschel
NSF Review, LLO

## Slide 2: Challenges
Nature of a new physics experiment
  Not all requirements are known upfront
  Past experience only goes so far
Geographically distributed team
  Caltech, MIT, AEI, Birmingham, ANU, LLO, LHO, LSC institutions
  Designers become testers and installers, then commissioners

## Slide 3: Major Remaining Technical Risk
Complexity of seismic isolation and suspensions
  Virgo experience: Commissioning a highly complex isolation system takes a long time
  Limited experience with monolithic suspensions at low noise
Core optics: coatings, thermal noise and absorption
High power operations
Controls
  Number of control loops an order of magnitude larger than initial LIGO
  Reliable and robust controls of interferometer

## Slide 4: Approach
Start from the front: Michelson test at LLO (L1)
  Build laser, mode cleaner, vertex chambers and optics
  Test PSL, HAM isolation, interferometer sensing and control
  Should have decent phase sensitivity
Start from the back: One arm cavity test at LHO (H2 Y-arm)
  Build a single arm cavity and inject light from the end
  Test BSC isolation, part of the locking scheme
  Look at stability
Beyond first year:
  Get L1 interferometer up as fast as possible
  H2 and H1 staggered by about half intervals behind L1

## Slide 5: Advantages
Reduce a lot of technical risk early
  A lot of systems need to get installed at least once in the first year
  All teams have to be on site
Get some early feedback on our designs
  Seismic isolation and suspension performance
    Low frequency: One arm test
    High frequency: Michelson test
  Optics: Coating quality
  Laser performance: Acoustic enclosure, high power
  Sensing and control: new digital controls system

## Slide 6: Interaction between Installation and Integration
Dedicated installation periods
  Coordination between different installation teams
  This is what we have right now
Dedicated commissioning periods
  Commissioning takes lead
  Limited installation tasks relegated to mornings or of no impact
  One arm test: October ‘11 to January ’12
Shared installation/commissioning periods
  Early shift: installation
  Late shift and weekends: commissioning
  Mid/Late 2010: Cooperation with H1 squeezer test

## Slide 7: Overview of H2 One Arm Test
BSC ISI
HEPI
HEPI
Quad SUS
TrMon SUS
ACB
Frequency stabilization w/ reference cavity
1064 / 532 nm NPRO
BSC ISI
HEPI
HEPI
Quad SUS
ITM
Triple SUS
FM
ACB
ETM
TM
LVEA:
No PSL
Test Mass optical lever (not shown)
Y-End
Arm Cavity length & alignment sensing

## Slide 8: H2 One Arm Test
New lock acquisition strategy developed for aLIGO
  Arm Length Stabilization system controls each arm cavity, putting them off-resonance
  The 3 vertex lengths are controlled using robust RF signals
  Arm cavities are brought into resonance in a controlled fashion

## Slide 9: Technical Objectives of H2 One Arm Testing Phase
BSC seismic isolation, quad suspension & transmission monitor
  Verification of the installation and alignment process
Develop robust locking with the ALS laser
  Wide-band feedback to the laser for easy locking; the low-frequency control (< 10 Hz) sent to the quad suspension to stabilize the arm length
  Characterize alignment stability (cavity will be outfitted with wavefront sensors)
    Active stabilization of ALS beam alignment required?

## Slide 10: Technical Objectives of H2 One Arm Testing Phase
Characterize and fine-tune low frequency performance of the ISI (seismic isolation)
  First chance to look at what is really important: relative fluctuations over 4 km baseline
  Trade-offs in the seismic isolation between very low frequencies (<~ 0.1 Hz) and mid-frequencies (1-few Hz) can be explored with the arm cavity
  Implement adaptive feed-forward controls to further minimize the arm length fluctuations

## Slide 11: Intermediate and Quantitative Goals of One Arm Test
Initial alignment: Sustained flashes of optical resonances in the arm cavity.
Cavity locking/ISC: Green laser locked to cavity for 10 minutes or more.
TransMon/ALS: Active beam pointing error on the TransMon table below 1 urad rms in angle and below 100 um rms in transverse motion.
SEI: Relative motion at the suspension point between the two SEI platforms below 250 nm rms (without global feedback).
Cavity length control (SEI/SUS/ALS): Relative longitudinal motion between ITM and ETM below 10 nm rms for frequencies below 0.5 Hz.
Cavity alignment fluctuations (SEI/SUS): Relative alignment fluctuations between the TIM and ETM below 100 nrad rms for frequencies above 0.1 Hz (without global feedback).

## Slide 12: Intermediate and Quantitative Goals of One Arm Test (cont.)
Controls (SUS): Decoupling of length-to-angle at the level of 0.05 rad/m or less, for frequencies below 0.5 Hz.
Controls (ISC): Fully automated cavity locking sequence; long term cavity locking.
TCS: Ring heater wavefront distortion, as measured by the Hartmann sensor, in agreement with the model at the 10 nm rms level.
Optical levers: Optical lever long term drift below 1 urad.
Calibration: ETM displacement calibration at the 20% level.
ALS: Ability to control frequency offset between 1064 nm and 532 nm resonances at the 10 Hz level.
ALS: Relative stability of the 1064 nm and 532 nm resonances at the 10 Hz level for frequencies below 0.5 Hz.

## Slide 13: Personnel
Adv. LIGO Management
  Carol and David
Installation leaders
  Mike (LHO) and Brian (LLO)
Commissioning leadership
  System lead: Peter
  LLO vertex test: Valera
  LHO one arm test: Daniel
Commissioning team
  Current LHO Team: Bram Slagmolen (ANU visitor), Keita Kawabe, Dani Atkinson, Victor Bigea, students from WSU and Columbia
  8-9 people total dedicated from LIGO lab for one arm test

## Slide 14: One Arm Cavity Test Schedule Installation Phase
ITMY (Input Test Mass Y-arm)
  February/March ’11: Install HEPI (Hydraulic External Pre-Isolator)
  May-July ‘11: Install SEI and SUS (Seismic and Suspension)
  August ‘11: Checkout
  September/October `11: Acceptance
ETMY (End Test Mass Y-arm)
  March/April ’11: Install HEPI
  June-August ‘11: Install SEI and SUS
  August ‘11: Install AOS (Auxiliary Optics Support)
  August ‘11: Install ISC (Interferometer Sensing and Controls)
  September ‘11: Checkout
  October/November `11: Acceptance

## Slide 15: One Arm Cavity Test Schedule Integration Phase
One Arm Cavity Test:
  October ‘11 to January ’12: Dedicated commissioning time
  February to May ’12: Shares installation and commissioning time
Second half of ’11:
  PSL (Pre-Stabilized laser), no impact
Starting February ’12:
  IMC (Input Mode Cleaner)

## Slide 16: Overview of L1 Pre-Stabilized Laser, Input Mode Cleaner, and Input Optics Integrated Test
Components:
PSL operational at maximum power of 165 W
Input optics: phase modulator, power control, Faraday isolator
Suspended Input Mode Cleaner, auxiliary optics, power recycling cavity optics
Seismic isolation: HEPI and ISI for HAM2/3, HEPI and passive stack for HAM
AOS: stray light baffles and optical levers
Ifo reflected port in-vac readout
Input optics in-air optical table 1
Input optics in-air optical table 2

## Slide 17: L1 PSL/IO/IMC Test
Main function of the IMC is the spatial filtering of the PSL light
The IMC also provides the frequency reference before the common arm signal is available
The IMC control scheme is the same as in initial LIGO
Much better isolation from the ground motion down to ~0.5 Hz

## Slide 18: Technical Objectives of L1 PSL/IO/IMC Testing Phase
Achieve robust operation of the IMC and noise performance sufficient to move to the next commissioning phase
  In-air locking at low power for initial alignment of IMC, FI, and PR optics
  In-vacuum locking at ~5 W to optimize the control loops: length, angular, local damping
High power operation up to 165 W – look for problems
  Evaluate the thermal effects in IMC and FI: transmission, isolation ratio, absorption, mode distortion, drift
  First assessment of the outer loop laser amplitude stabilization

## Slide 19: Technical Objectives of L1 PSL/IO/IMC Testing Phase
Characterize the noise
  PSL frequency noise
  IMC angular motion
  Power fluctuation on the IMC transmitted light
Optimize low frequency performance of the seismic isolation
  Use adaptive feed forward to minimize the relative motion of HAM2/3
  Evaluate the necessary VCO range to minimize the phase noise out of the PSL

## Slide 20: Intermediate and Quantitative Goals of L1 PSL/IO/IMC Test
IMC availability >90% with mean lock duration of >4 hours
Fully automated locking sequence
PSL to PRM power transmission > 75%
Longitudinal control bandwidth ~40 kHz
Frequency/length feedback cross over frequency ~10 Hz
Angular control bandwidth ~1 Hz
IMC transmitted beam angular motion rms <1.6 urad (1/100 of the cavity angle)

## Slide 21: Intermediate and Quantitative Goals of L1 PSL/IO/IMC Test (cont.)
IMC transmitted light power fluctuation <1% rms
IMC transmitted light RIN <1e-7/rtHz
IMC visibility >95%
FI isolation ratio at full power 30 dB

## Slide 22: Personnel
LLO Commissioning team
  Commissioning leader: VF
  Commissioning team: Joe Betzweizer, Suresh Doravari, Chris Guido, Keith Thorne (LLO CDS), David Feldbaum (UF), Matt Heintze (UF), Ryan de Rosa (LSU), Anamaria Effler (LSU)
  7-8 LIGO lab personnel including 2-3 visitors from CIT/MIT during the PSL/IO/IMC test

## Slide 23: PSL/IO/IMC Test Schedule
  June/July `11: Install input/output vacuum tubes, septum plates
HAM1
  February/June `11: Install HEPI
  July/August `11: Install passive stack
  September `11: Install ISC
  October/December `11: Acceptance
HAM3
  February/June `11: Modify HEPI
  August `11: Install ISI
  September `11: Install SUS
  October/January `12: Acceptance

## Slide 24: PSL/IO/IMC Test Schedule (cont.)
HAM2
  February/June `11: Modify HEPI
  August/September `11: Install ISI
  October/November `11: Install SUS and Optics
  January/March `12: Acceptance
  September `11: AOS (stray light baffles)
January `12: Start of PSL/IO/IMC testing
May `12: Start of corner Michelson testing