## Sheet1
SUMMARY OF SUSPENSION FINAL DESIGN REVIEWS
| Norna A Robertson | 9th April 2014
| T1200463-v14 | [5 empty] | Background information on these comments can be found in T1200492.
Mechanical
Review # | Type of Suspension | Name of Review | Date | Document ref. (e.g. final design doc) | web page(s) | Report ref. | Comments | Review #
1 | ETM/ITM | Final Design Review for the Mechanical Elements | 2008 | T1000286-v9, T1000404 | https://awiki.ligo-wa.caltech.edu/aLIGO/Quad_Suspensions/FDR, http://www.eng-external.rl.ac.uk/advligo/Reviews/Quad%20suspension%20FRR.htm |  | Formal report not completed. Authorisation to proceed was given. See item 7 for further review on this topic which supercedes this review. | 1
2 | ETM/ITM | Final Design Review (FDR) and Fabrication Readiness Review (FRR) for the Structural Weldments | April 2008 | T1000286-v9, T1000410 | https://awiki.ligo-wa.caltech.edu/aLIGO/Quad_Suspensions/FDR | L080026 | Actions completed. | 2
3 | ETM/ITM | Monolithic Stage Final Design Review | Sept 2010 | G1000785-v1 T1000337-v4 |  | L1000357-v3 | Essentially complete. Some documentation being completed with estimated date of Thanksgiving | 3
4 | ETM/ITM | Ear Fabrication Readiness Review | Jan 2010 | T0900447 |  | L1000003-v3 | Actions completed | 4
5 | ETM/ITM | Quad Monolithic Damage Mitigation Review | Nov 2011 onwards | E1101098, T1100563 |  | E1101098 | E1101098 now updated to v8 and all actions closed, 9th April 2014. | 5
6 | ITM | Gas Damping Technical Review Board | Feb 2010 onwards | T1000667-v5, M1000030-v1 |  | T1000175-v2 | Redesigned thin CP has been implemented. Further gas damping mitigation is on liens list under FMP. | 6
7 | BSC Suspensions (ETM/ITM Quad & BS/FM) | Assembly Review | May-Sept 2011 | T1100254-v11 | https://awiki.ligo-wa.caltech.edu/aLIGO/BSC%20Suspensions%20%28quad%2C%20BS/FM%29%20Assembly%20Review | T1100254-v13 | T1100254-v13 now uploaded (25 Feb 2014). All items are closed with exception of item B4 about modeling cross-coupling and its effect on control. This is ongoing work which will continue as part of interferometer controls work. | 7
8 | BSC Suspensions (ETM/ITM Quad & BS/FM) | Technical Review Board: Decision on Elimination of Eddy Current Dampers on Top Masses of Suspensions | June 2011 | T1100342-v1 |  | T1100342-v1 | Actions completed | 8
9 | BS/FM | Final Design and Fabrication Readiness Review | Sept 2008 | T080218-v2 | https://awiki.ligo-wa.caltech.edu/aLIGO/BS_Suspension, http://www.eng-external.rl.ac.uk/advligo/Reviews/bs_review.htm |  | Formal report not completed. Authorisation to proceed was given. See item 7 for further review on this topic which supercedes this review. | 9
10 | BS/FM | Review of Design and Procedure for Use of BS/FM Prism Jig | Feb 2012 | E1000753-v4 | https://awiki.ligo-wa.caltech.edu/aLIGO/Prism_jig_review | T1200105-v2 | Actions completed | 10
11 | HLTS | Final Design Review | April 2010 | T1000012-v1 | https://awiki.ligo-wa.caltech.edu/aLIGO/HLTS_Design_Reviews#FDR | M1000126-v3 | Sotware review was requested. Will be covered in acceptance review. | 11
12 | HSTS | Final Design Review | Oct 2009 - Jan 2010 | T0900435-v3 | https://awiki.ligo-wa.caltech.edu/aLIGO/IMC_Design_Reviews#FDR | M0900321 | Actions done from T0900435. Actions done from M0900321. | 12
13 | OMC-SUS | Final Design Review | April 2009 | T0900060-v1 | https://awiki.ligo-wa.caltech.edu/aLIGO/OMC_Suspension/Final_Design_Review | L0900064-v5 | Actions completed. | 13
14 | HLTS and HSTS | HLTS and HSTS Assembly Review | Nov 2011- Feb 2012 | T1100593-v10 |  | T1100593-v10 | Actions completed | 14
Electronics
15 | BOSEMs | Final Design Review and Fabrication Readiness Review | Feb-March 2008 | T050111-v4 | https://awiki.ligo-wa.caltech.edu/aLIGO/BOSEM_FRD_and_FRR | L080022-00 | Actions completed. | 15
16 | AOSEMs | Final Design Review and Fabrication Readiness Review | June 2009 | T0900286-v2 | https://awiki.ligo-wa.caltech.edu/aLIGO/OSEMs | L0900116-v6 | Documentation updated as captured in DCN E1300492. actions completed. | 16
17 | UK SUS Electronics Subsystems: Satellite Amplifier and OSEM Interface | Fabrication readiness review | July 2009 | T0900261-v1 |  | L0900141-v3 | Actions completed. | 17
18 | Top Mass Stage (TOP) Driver Electronics (quad and triple): UK | Readiness for Fabrication Review | June 2009 | T0900170-v1 |  | L0900098-v4 | Actions completed. | 18
19 | Triple Acquisition-Mode Driver Electronics: UK | Recommendation for Fabrication Review | Oct 2009 | T0900315-v1 |  | L0900209-v3 | Actions completed. | 19
20 | Delivery of Electrostatic Drivers from UK | RODA | Nov 2009 | M0900293-v1 |  | M0900293-v1 | Items delivered as per RODA. | 20
21 | ESD Cabling, Bonding, Soldering | Design review | July 2011 | T1100349, T1100320, L1100158-v1 | https://awiki.ligo-wa.caltech.edu/aLIGO/ElectroStaticDrive |  | Actions completed. T1100349 updated to v3. T1100320 updated to v4. | 21
22 | HAM Suspensions Electronics | Final Design Review | April 2010 | T1000061-v6 | https://awiki.ligo-wa.caltech.edu/aLIGO/HLTS_Design_Reviews#FDR | M1000126-v3 | This item is covered under item 11 above ( reviews were combined) | 22
23 | Output Mode Cleaner (OMC) Driver Electronics | Fabrication readiness review | Jan 2010 |  |  | L1000020-v2 | Actions completed. | 23
24 | TransMon Driver Electronics | Fabrication readiness review | Jan 2010 |  |  | L1000021-v1 | Actions completed. | 24
25 | PUM Driver Electronics | Fabrication readiness review | Sept 2009 |  |  | L0900169-v4 | Actions completed. | 25
26 | Coil Driver and Monitor Electronics: Upper Intermediate Mass Stage (UIM) | Fabrication readiness review | May 2009 |  |  | L0900093-v3 | Actions completed. | 26