## Active Requests
E1500229 Third IFO Component Loan Log - ACTIVE REQUESTS
2016-09-06 | today's date | [7 empty] | 491693 | implicit escrow total
Request | status | start | end | extention | loan value | released? | follow-up | returned? | escrow value | comments
E1500227 | approved | 2015-04-27 | 2015-07-01 | 2017-01-20 | 7813 | yes | 2016-12-20 | no | 7813 | 1/26/16 Component request combined with E1500399. 4/28/2015 quote from Physik Instrumente: qty 1 S-330.4SD Piezo Tip/Tilt Platform, 5mrad (10 mrad Optical), Closed-Loop, Sub-D Delivery is ~ 4 weeks ARO . PSL-PZT Actuator . 03/15/16 - Per Rick S. At CIT. Should be ready for return. 04/25/16 - Spoke to Rick. He is going to check on the return.
E1500231 | approved | 2015-04-27 | 2015-09-01 | 2016-08-01 | 170000 | yes | 2016-07-01 | no | 170000 | 1/26/16 Waiting for LLO to complete the installation then will have to have the boards from LLO modified before returning to 3rd IFO. The primary delay was commissioning not allowing installation of components at LLO. Return date should be changed to 8/1/16.
E1500298 | approved | 2015-07-16 | 2016-01-01 | 2017-01-01 | 16000 | yes | 2016-12-01 | no | 16000 | 1/26/16 - The two busted PMC’s are still being investigated and then still need to be reworked and rebuilt and then sent to LLO before the 3rd IFO one is released. I have no time frame on this work and it could quite easily be another year until this is complete. 03/15/16 - The two 3IFO PMCs. One at LLO as hot spare. One in LHO Lab being worked on.
E1500399 | approved | 2015-10-01 | 2016-01-01 | 2017-01-01 | 18000 | yes | 2016-12-01 | no | 18000 | 1/26/16 Staff only just identified (Alena Ananyeva) to work this. Work not started. Estimated work will start Feb 2016 and last 9 months. Return date should be changed to 1/1/2017
E1500430 | approved | 2015-11-02 | 2016-11-01 |  | 40000 | yes | 2016-10-01 | no | 40000 | OFI Assembly - Shipped eLIGO weldment to LLO. This was not a 3IFO part. 01/29/16 - Gerardo shipped the internal parts for the OFI (from 3IFO inventory) on ICS shipment load #7973.
E1600026 | approved | 2016-01-26 | 2016-07-01 |  | 10000 | yes | 2016-06-01 | no | 10000 | View Ports - Shipped 01/28/16, Shipment load # 7969
Prior to F1500003 | approved | 2015 | 2016 |  | 49500 | yes | 2016-09-01 | no | 49500 | 14 OpLev lasers. 4 - (HAM2-5) at Mid-X. 9 - Jason has for testing and will return when ready for storage. 1 - is owed to 3IFO, Jason will supply the LHO spares. 06/17/2016 Value based on old cost of $5500.00/each. Trying to get current price.
Prior to F1500003 | approved | 2015 | 2016 |  | 117000 | yes | 2016-09-01 | no | 117000 | ASC RFPD (x4), LSC RFPD (x2), DCPD for OMC (x2), Fast Shutter for ISC, Rich Abbott. Checked out and stored at CIT.
Prior to E1500003 | approved | 2015 | 2016 |  | 12000 | yes | 2016-09-01 | no | 12000 | SEI Chassis checked out by Ops. These are in test stands and in lab being modified for Hardware watchdog work.
E1500460 | approved | 2016-02-01 | after 02 |  | 55000 | Yes |  |  | 51380 | 1/26/16 pending with Jeff. 04/25/16 - Spoke with Jenne, Geophones will be needed soon. 06/14/2016 Gave 6 L4Cs to David M. S/Ns are L41432, L414334, L41426, L41444, L41423, L414443. The remaining L4Cs will be given out as they are needed. Valuing the L4Cs at $1835.00 each. 06/21/2016 - A total of 28 L4C have been given to David M.
follow-up - red date indicates scheduled follow-up, black date indidicates follow-up attempt

## Inactive Requests
E1500229 Third IFO Component Loan Log - INACTIVE REQUESTS
2016-09-06 | today's date
Request | status | start | end | extention | value | released? | follow-up | returned? | comments
E1600002 |  | 2016-01-16 | 2016-07-06 |  |  | HOLD |  |  | PSL/IO Periscope. On hold. May not be needed.
E1600138 | closed/ SPARE | 2016-05-06 | 2016-08-01 |  | 12500 | NO |  | no | 5 PSL HPO Laser Crystals - Peter K. shipped to LLO. Due to be replaced when LLO receives rplacement crystals in 08/2016. 05/25/16 - Peter K. & Jeff B. Searched the 3IFO and spare inventory accounted for a full set of laser crystals. (9 total 4 for the laser and 5 are spares). It was agreeded these 5 crystals came out of LHO spares and not 3IFO. This request can be closed.
E1500447 | closed/ SPARE | 2016-03-01 |  |  | 22000 | HOLD |  |  | The Tiptilts are borrowed from spares inventory, NOT 3IFO inventory. There is a request for cables from 3IFO inventory not listed on this form. 01/28/2016 Checking with Dennis for approval of change.
E1500462 | closed/ SPARE | 2016-02-01 | after 02 |  | 2500 | HOLD |  |  | 1/26/16 pending with Jeff. 04/25/16 - Spoke with Jenne, AA chassis will be needed soon. 06/21/2016 Per Richard McCarthy - This AA chassis (S/N S1203144) did not come from 3IFO. It was pulled from LHO spares. This request can be closed.
E1500461 | closed/ NOT NEEDED | 2016-02-01 | after 02 |  | 15050 | CLOSE |  |  | 1/26/16 pending with Jeff. 04/25/16 - Spoke with Jenne, IO chassis may not be needed. 06/21/2016 - Per Jenne This IO chassis is not needed. This request can be closed.
E1600025 | closed/ NOT NEEDED |  |  |  |  | No |  |  | 01/28/2016 We cannot supply the parts being requested. Only two sets of the Walking plates and the Platform A-D were manufactured for each site. There are no spares. Sent note to Dennis & Janeen.
E1500472 | closed/ SPARE |  |  |  |  | No |  |  | We think that there are copious spares. If no spares exsist (after careful search) then a loan from 3rd IFO stock is approved with the stipulation that the unit must be returned. 01/28/16 note to Betsy to clairify cable request. 04/25/16 - These cables did NOT come from 3IFO stocks.
E1500317 | rejected |  |  |  |  | No |  |  | HAM ISI request not approved - blade testing purpose to be performed at LASTI.
E1600072 | closed | 2016-03-01 | 2016-03-21 |  |  | yes |  | yes | This loan can be closed. 03/29/2016 Returned the 3 SLEDs to TCS Box 10. S/Ns for the 840-5 are 12.02.45, 12.02.47, for the 790-5 are 11.10.52, 11.10.39
E1600235 | closed/ NOT NEEDED | 2016-08-01 | 2016-08-30 |  |  | yes |  | yes | This loan can be closed. Mirror not used so returned to 3IFO storage.
prior to F1500003 | closed/ SPARE | 2016-03-14 | 2016 |  | 6000 | yes | 2016-09-14 | no | Part No # 9722012, 7.8" Viewport S/N 001. Released to Gerardo per E-Mail, with paperwork to follow.Confirmed with Joe and Gerardo - this came from SPARE BW Aug 31, 2016
E1600090 | approved/ SPARE | 2016-03-25 | 2016 |  |  | yes | 2016-09-25 | no | DCC #D1101005 S/N 20 - 6" HQ 0.75deg VP Optic. 04/25/16 - Shipped to LLO on ICS shipment load #8102. - Confirmed that it came from SPARE Joe D/Betsy Aug 30, 2016
E1600034 | closed/ RETURNED | 2016-02-01 | 2016-05-01 |  | 2000 | yes | 2016-09-01 | no | Ring Heater Cables - Shipped to LLO, ICS shipment load #7982. Returned from LLO to LHO - placed back in 3IFO storage. BW -Sept 2016
follow-up - red date indicates scheduled follow-up, black date indidicates follow-up attempt